## Guideline
About The T+1 Industry Implementation Playbook Activity Tracker
The T+1 Industry Implementation Playbook provides timelines, milestones, and guidelines for market participants to assist in the planning, development, testing, and migration to a T+1 settlement cycle. The Playbook sections lalso provide suggested activities across a number of business areas, including trade processing, asset servicing, documentation, securities lending, prime brokerage, and funding and liquidity. The T+1 Industry Implementation Playbook Activity Tracker (this excel) is designed to maintain lists of activities for each section and sub section of the playbook.
Before getting started, it is recommended to take a look at the sample data provided.
How do I get started?
The activity matrix structure is listed below:
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
Line Number | For each activity, implementation steps are provided as a guide for organizations as they conduct readiness activities in preparation for the migration to T+1 settlement (Note: Certain implementation steps will not be applicable to each organization). | This column under each of the activities tables is intentionally left blank to allow users of the Playbook to choose which organization participants are responsible for specific implementation steps. This will allow users to customize the table to align with their organization’s needs and to accurately reflect their organization’s structure. | This column under each of the activities tables is intentionally left blank to allow users of the Playbook to choose which systems apply to specific implementation steps. This will allow users to customize the table in order to align with their organization’s needs and to accurately reflect their organization’s structure.
Market participants that choose to utilize activity matrices should assess and capture their respective organization’s requirements and structure within the Organization Participants and Systems columns. An example of a “completed” activity table is below:
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
1 | Inventory trading systems, including hardware and software | All | Internal, Vendor
2 | Determine systems with in-scope products impacted by T+1 implementation | All | Internal
3 | Examine changes required to systems for settlement date configuration | IT | Internal
4 | Assess impact of required changes to upstream and downstream systems | All | Internal
5 | Determine responsibility for trading system changes | Front, IT | Internal, Vendor
6 | Coordinate system changes with internal and external stakeholders | All | Internal, Vendor
7 | Develop trading system and operations test plans | Middle, Back, IT, Vendor | Internal, Vendor
8 | Schedule and execute system changes | IT, Vendor | Internal, Vendor
The index tab lists down all the activity matrices for each section and sub section as listed in the playbook.

## Index
Index
Introduction
1.2.7. | Baseline Metrics for T+1
Trade Processing
3.3.1 | Trading Systems and Reference Data
3.3.1.A. | Activities to Configure Trading Systems
3.3.1.B. | Activities to Update Reference Data
3.3.1.C. | Activities to Review Trade Funding Processes and Payment Mechanisms
3.3.1.D. | Activities to Revise Mutual Fund Settlement Dates
3.3.1.E. | Activities to Update ETF Primary Market Create and Redeem Processes
3.3.1.F. | Activities to Review Trade Order Management and Trade Capture Processes
3.3.1.G. | Activities to Standardize Communication Protocols for Trade Away Processes
3.3.2 | Trade Matching
3.3.2.A. | Activities to Update Trade Matching Processes
3.3.2.B. | Activities to Align to Industry-Recommended Allocation Timelines
3.3.2.C. | Activities to Configure Purchase and Sales Systems (PNS) and Institutional Processing Systems for Near-Time Matching
3.3.3 | Trade Affirmation
3.3.3.A. | Activities to Review Trade Affirmation Processes
3.3.3.B. | Activities for Changes to the Timing of NSCCs CNS Projection Reports
3.3.3.C. | Activities to Align to Industry-Recommended Affirmation Timelines
3.3.3.D. | Activities to Standardize Communication Protocols Among Affirming Parties
3.3.4 | Physical Securities
3.3.4.A. | Activities to Decommission Physical Securities
3.3.4.B | Activities to Adjust Processes and Systems Related to Physical Securities
Asset Servicing
4.3.1 | Ex-Date Changes
4.3.1.A. | Configure Ex-Date Changes
4.3.1.B. | Adjust Ex-Date Notification Announcement Systems
4.3.1.C. | Modify Internal Processing Systems that Calculate Ex-Dates
4.3.1.D. | Adjust Due Bill Processing
4.3.1.E. | Modify Interim Accounting Processes
4.3.2 | Cover / Protect Date Determination
4.3.2.A. | Review Reorganization Announcement Platform
4.3.2.B. | Modify Voluntary Reorganization Processing Applications
4.3.2.C. | Update Internal Processing Systems that Consume Cover / Protect Dates
4.3.2.D. | Adjust Stock Record Platforms as Necessary
4.3.4 | Dividend Reinvestment Plans
4.3.4.A. | Assess Dividend Reinvestment Plans
Documentation
5.3.1 | External Documentation
5.3.1.A. | Update External Client-Facing Documentation
5.3.1.B. | Update External Service Agreement Documentation
5.3.1.C. | Determine Impact of E-Delivery for Client Groups
5.3.2 | Internal Documentation
5.3.2.A. | Adjust Operating Procedures and Internal Control Documentation
5.3.3 | Customer and Staff Education
5.3.3.A. | Educate Customers and Staff on T+1 Settlement
Securities Lending
6.3.1 | Securities Lending Processes and Procedures
6.3.1.A. | Determine Impact on Securities Lending Processes and Procedures
6.3.2 | Stock Loan Recall
6.3.2.A. | Align to Updated Stock Loan Recall Timing Changes
6.3.3 | Margin Calculations Processes
6.3.3.A. | Update Margin Calculations Processes
6.3.4 | Master Securities Loan Agreement
6.3.4.A. | Updating Master Securities Loan Agreement
6.3.5 | Regulatory Considerations
6.3.5.A. | Assess Regulatory Considerations related to Securities Lending
Prime Brokerage
7.3.1 | Review Client Onboarding Documentation and Processing Dependencies
7.3.1.A. | Review Prime Broker Disaffirmation Timelines
7.3.1.B. | Review Prime Broker Affirmation Timelines
Funding and Liquidity Considerations
8.3.1 | Liquidity and Collateral Management
8.3.1.A | Assess Liquidity and Collateral Management
8.3.2 | Forex Considerations and Funding
8.3.2.A. | Assess Forex Considerations and Funding
8.3.3 | Intraday & End of Day DTCC Settlement Processing
8.3.3.A. | Assess Intraday & End of Day DTCC Settlement Processing
Additional Considerations
9.3.1 | Global Considerations
9.3.1.A. | Assess Processes for Global Considerations
9.3.2 | Options Exercise and Assignment
9.3.2.A. | Assess Options Exercise and Assignment Processes
9.3.3 | Primary Offerings
9.3.3.A. | Assess Primary Offerings
9.3.4 | Reconciliations for Errors / Fails
9.3.4.A. | Assess Reconciliation Processes for Errors / Fails
9.3.5 | Buy-Side Considerations
9.3.5.A. | Assess Buy-Side Considerations
Testing and Migration
11.3.1. | Develop Internal and Industry Test Plans
11.3.1.B. | Activities to Develop Test Plans

## Baseline Metrics
Baseline Metrics for T+1
T+1 Baseline Metrics
Metric Category | Metric | Dimensions
|  | Count/ Value | Product | Legal Entity/Line of Business
Trade Volume | U.S. Equities/DTCC eligible products
Fixed income (e.g., US treasuries/Bonds)/ DTCC population
ETFs/Exchange Traded Note (ETNs)
ADRs/Master Limited Partnerships (MLPs)
Fail Rates | Metrics for trades unmatched from T+1:
Due to SSI mismatch
Due to product not being setup
Due to inventory
Due to counterparty missing instructions
Due to mismatch on trade details
Due to ongoing corporate action event
Fails resolved by manual intervention
Fails resolved by client sending correct trade file
Fails resolved by counterparty matching
Fails due to trades being “don’t know’d” (DK'd)
Average time to resolve fail
Allocation Rates | Average Daily Count of Allocations
Allocated on T
Allocated on T+1
Allocated on T+2
Percentage of allocations on trade date (T) after 7:00PM ET
Number of clients not sending trades on T
Affirmation Rates | Average Daily Affirmation Rate
Affirmed on T
Affirmed on T+1
Affirmed on T+2
Percentage of affirmations done after 9:00PM ET on T
Buy-in (DTC) | Number of buy-in due to insufficient stock
Number of buy-in due to no locate in place
Buy-in due to settlement error
Number of buy-in due incorrect place of settlement (e.g., trade booked in Italy instead of DTC)
Trade Errors | Number of Trades manually touched everyday
Reason for trades being manually touched
Trade failed due to manual error
Corporate Actions | Average volume of corporate action events
Securities Lending | Bi-lateral Trades (daily, weekly, monthly, etc. for all)
Margin/Exposure/Collateral management
Contract Compare breaks
Delivery versus Payment (DVP) vs Free of Payment (FOP)
Recalls (Securities Industry Automation Corporation (SIAC), etc.)
Reg SHO 204 (failure to deliver)
Payments | Number of manual checks
Average ACH timing
Average ACH volumes

## Trade Processing
Trading System and Reference Data |  |  |  | Trade Matching |  |  |  | Trade Affirmation |  |  |  | Physical Securities
3.3.1.A. Activities to Configure Trading Systems |  |  |  | 3.3.2.A. Activities to Update Trade Matching Processes |  |  |  | 3.3.3.A. Activities to Review Trade Affirmation Processes |  |  |  | 3.3.4.A. Activities to Decommission Physical Securities
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
1 | Inventory trading systems, including hardware and software (completeness check) |  |  | 1 | Ensure that systems and reference data related to trade matching are included in inventories for configuration |  |  | 1 | Ensure that systems and reference data related to trade affirmation are included in inventories for configuration |  |  | 1 | Inventory platforms supporting physical securities delivery
2 | Determine systems with in-scope products impacted by T+1 implementation |  |  | 2 | Examine upstream system, data, and process changes to ensure that they do not interfere with the process for trade matching |  |  | 2 | Examine upstream system, data, and process changes to ensure that they do not interfere with the process for trade affirmation |  |  | 2 | Determine platforms supporting physical securities delivery impacted by T+1 implementation
3 | Examine changes required to systems for settlement date configuration (e.g., hardcoding vs. logic in programs) |  |  | 3 | Determine changes required to processes related to trade matching |  |  | 3 | Determine changes required to processes related to trade affirmation and new cutoff time |  |  | 3 | Assess changes required to decommission platforms supporting physical securities delivery for T+1 settlement
4 | Assess the impact of required changes to upstream and downstream systems |  |  | 4 | Coordinate changes to processes related to trade matching with internal and external stakeholders |  |  | 4 | Coordinate changes to processes related to trade affirmation with internal and external stakeholders |  |  | 4 | Determine responsibility for platform changes (proprietary vs. external vendor and service bureau)
5 | Determine responsibility for trading system changes (proprietary vs. external vendor and service bureau) |  |  | 5 | Develop test plans for trade matching |  |  | 5 | Develop test plans for affirmed and unaffirmed eligible institutional trade submission, prime broker transactions, and ID Net transactions |  |  | 5 | Coordinate platform changes with internal and external stakeholders
6 | Coordinate trading system changes with internal and external stakeholders |  |  | 6 | Schedule and execute process changes for trade matching |  |  | 6 | Schedule and execute process changes for affirmed trade submission |  |  | 6 | Develop test plans for decommissioning physical securities delivery
7 | Develop trading system test plans | [6 empty] | 7 | Utilize services (e.g., ITPs M2i) to achieve maximum affirmations |  |  | 7 | Schedule and execute changes to decommission physical securities
8 | Schedule and execute system changes (consider customer experience and user interface continuity when scheduling trading system changes) |  |  | 3.3.2.B. Activities to Align Industry-Recommended Allocation Timelines
|  |  |  | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | 3.3.3.B. Activities for Changes to the Timing of NSCCs CNS Projection Reports |  |  |  | 3.3.4.B. Activities to Adjust Processes and Systems Related to Physical Securities
3.3.1.B. Activities to Review Trade Funding Processes and Payment Mechanisms |  |  |  | 1 | Ensure that systems and reference data related to trade allocations are included in inventories for configuration |  |  | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | 2 | Examine upstream system, data, and process changes to ensure that they do not interfere with the process for trade allocations |  |  | 1 | Inventory projection reports, including created projection reports and those received and used from other organizations (i.e., cash projection reports, CNS Projection Report) |  |  | 1 | Inventory platforms supporting physical securities delivery
1 | Ensure that systems and reference data related to trade funding, as well as payment mechanisms, are included in inventories for configuration |  |  | 3 | Determine changes required to processes related to trade allocations |  |  | 2 | Assess projection reports for changes from T+1 settlement |  |  | 2 | Determine platforms supporting physical securities delivery impacted by T+1 implementation
2 | Examine upstream system, data, and process changes to ensure that they do not interfere with the process for trade funding |  |  | 4 | Coordinate changes to processes related to trade allocations with internal and external stakeholders |  |  | 3 | Determine if settlement date changes to projection reports will be automatically captured or need to be manually updated |  |  | 3 | Assess changes required to platforms supporting physical securities delivery for T+1 settlement
3 | Determine changes required to processes related to trade funding including any global trade funding |  |  | 5 | Develop test plans for trade allocations |  |  | 4 | Coordinate changes to projection reports with internal and external stakeholders |  |  | 4 | Determine responsibility for platform changes (proprietary vs. external vendor and service bureau, issuers)
4 | Assess how changes to payment mechanisms impact policies, procedures, and controls |  |  | 6 | Schedule and execute process changes for trade allocation timelines |  |  | 5 | Develop test plans for activities related to projection reports |  |  | 5 | Coordinate platform changes with internal and external stakeholders
5 | Develop capacity for mobile deposits or other electronic payment methods and recommend these methods to customers (consider efficiencies to decrease check and Automated Clearing House (ACH) processing time for retail investors) | [6 empty] | 6 | Schedule and execute changes for projection reports |  |  | 6 | Develop test plans for physical securities delivery for T+1 settlement
6 | Coordinate changes to payment mechanisms and processes related to trade funding with internal and external stakeholders |  |  | 3.3.2.C. Activities to Configure Purchase and Sales Systems for Near-Time Matching | [7 empty] | 7 | Schedule and execute changes to physical securities for T+1
7 | Develop trade funding process and payment mechanism test plans |  |  | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | 3.3.3.C. Activities to Align Industry-Recommended Affirmation Timelines
8 | Schedule and execute changes to trade funding and payment mechanism processes, policies, procedures, and controls |  |  | 1 | Ensure that systems and reference data related to Purchase and Sales systems for near-time are included in inventories for configuration |  |  | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
9 | Communicate changes to trade funding policies and procedures to customers |  |  | 2 | Examine upstream system, data, and process changes to ensure that they do not interfere with Purchase and Sales systems for trade matching |  |  | 1 | Ensure that systems and reference data related to trade affirmations are included in inventories for configuration
|  |  |  | 3 | Determine changes required to configure Purchase and Sales system processes for near-time trade matching |  |  | 2 | Examine upstream system, data, and process changes to ensure that they do not interfere with the process for trade affirmations
3.3.1.C. Activities to Review Trade Funding Processes and Payment Mechanisms |  |  |  | 4 | Coordinate changes to processes related to near-time trade matching with internal and external stakeholders |  |  | 3 | Determine changes required to processes related to trade affirmations
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | 5 | Develop test plans for configuration of Purchase and Sales systems for near-time matching |  |  | 4 | Coordinate changes to processes related to trade affirmations with internal and external Stakeholders
1 | Ensure that systems and reference data related to trade funding, as well as payment mechanisms, are included in inventories for configuration |  |  | 6 | Schedule and execute process changes for Purchase and Sales systems for near-time matching |  |  | 5 | Develop test plans for trade allocations, confirmations, and affirmations
2 | Examine upstream system, data, and process changes to ensure that they do not interfere with the process for trade funding | [6 empty] | 6 | Schedule and execute process changes for trade affirmation timelines
3 | Determine changes required to processes related to trade funding including any global trade funding
4 | Assess how changes to payment mechanisms impact policies, procedures, and controls | [6 empty] | 3.3.3.D. Activities to Standardize Communication Protocols Among Affirming Parties
5 | Develop capacity for mobile deposits or other electronic payment methods and recommend these methods to customers (consider efficiencies to decrease check and Automated Clearing House (ACH) processing time for retail investors) | [6 empty] | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
6 | Coordinate changes to payment mechanisms and processes related to trade funding with internal and external stakeholders | [6 empty] | 1 | Ensure that systems and reference data related to communication protocols among affirming parties are included in inventories for configuration (i.e., Trade Order Management Solution (TOMS), UTC)
7 | Develop trade funding process and payment mechanism test plans | [6 empty] | 2 | Determine changes required for affirming parties and relevant communication protocols
8 | Schedule and execute changes to trade funding and payment mechanism processes, policies, procedures, and controls | [6 empty] | 3 | Coordinate changes to processes related to affirming parties’ communication protocols with internal and external stakeholders (e.g., FIX)
9 | Communicate changes to trade funding policies and procedures to customers | [6 empty] | 4 | Develop test plans for standardized communication protocols among affirming parties
[8 empty] | 5 | Schedule and execute process changes for standardization of communication protocols among affirming parties
3.3.1.D. Activities to Revise Mutual Fund Settlement Dates
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
1 | Inventory mutual funds
2 | Determine whether to revise mutual fund settlement dates
3 | Assess changes required for mutual fund settlement date configuration
4 | Coordinate with DTCC to revise mutual fund settlement dates within Fund/SERV
5 | Develop test plans for settlement of mutual funds
6 | Schedule and execute mutual fund settlement date changes
3.3.1.E. Activities to Adjust ETF Create and Redeem Processes
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
1 | Review ETF Create and Redeem processes to meet agreed upon cut-off times
2 | Develop test plans for ETF creation and redemption
3 | Schedule and execute ETF settlement date changes
3.3.1.F. Activities to Review Trade Order Management and Trade Capture Processes
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
1 | Ensure that systems and reference data related to trade order management and trade capture are included in inventories for configuration (i.e., Trade Order Management Solution (TOMS), UTC)
2 | Determine changes required to processes related to trade order management and trade capture
3 | Coordinate changes to processes related to trade order management and trade capture with internal and external stakeholders (e.g., FIX, SWIFT)
4 | Develop test plans for trade order management and trade capture
5 | Schedule and execute process changes for trade order management and trade capture
3.3.1.G. Activities to Standardize Communication Protocols for Trade Away Processes
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
1 | Ensure that systems and reference data related to trade away processes are included in inventories for configuration (i.e., Trade Order Management Solution (TOMS), UTC)
2 | Determine changes required for trade away processes and relevant communication protocols
3 | Coordinate changes to processes related to trade away communication protocols with internal and external stakeholders (e.g., FIX)
4 | Develop test plans for standardize communication protocols for trade away processes
5 | Schedule and execute process changes for standardization of communication protocols for trade away processes

## Asset Servicing
Ex-Date Changes |  |  |  | Cover/Protect Date Determination |  |  |  | Dividend Reinvestment Plans
4.3.1.A. Activities to Configure Ex-Date Changes |  |  |  | 4.3.2.A. Activities to Review Reorganization Announcement Platforms |  |  |  | 4.3.4.A. Activities to Assess Dividend Reinvestment Plans
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
1 | Identify and inventory instances where ex- dates are generated or received |  |  | 1 | Ensure that reorganization announcement platforms and reference data are included inventories for configuration |  |  | 1 | Determine required changes for DRIPs due to T+1 settlement
2 | Conduct conversations with vendors and service bureaus to ensure that ex-dates are captured, tested, and approved |  |  | 2 | Evaluate the impact to downstream systems and processes (internal and external) for reorganization announcement platform changes |  |  | 2 | Determine required changes to issuance of DRIP shares (if open market purchases)
3 | Assess changes required to systems for capturing ex-dates |  |  | 3 | Determine responsibility for reorganization announcement platform changes (proprietary vs. external vendor and service bureau) |  |  | 3 | Determine required changes to DRIP communications resulting in shortened settlement cycle
4 | Review processes for corporate action events to determine impact of ex-date changes |  |  | 4 | Coordinate reorganization announcement platform changes with internal and external stakeholders |  |  | 4 | Develop test plans for DRIP changes for T+1 settlement
5 | Examine impact of ex-date changes to compliance and oversight requirements |  |  | 5 | Develop test plans for reorganization announcement platforms |  |  | 5 | Schedule and execute changes prior to T+1 settlement
6 | Ensure materials regarding T+1 ex-date implications are included in customer communication plans |  |  | 6 | Schedule and execute changes related to reorganization announcement platforms |  |  | 6 | Advise plan participants of changes to DRIP functionality
7 | Develop ex-date and corporate action event test plans
8 | Schedule and execute ex-date changes |  |  | 4.3.2.B. Activities to Modify Voluntary Reorganization Processing Applications
|  |  |  | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
4.3.1.B. Activities to Adjust Ex-Date Notification Announcement Systems |  |  |  | 1 | Ensure that systems and reference data related to voluntary reorganization processing are included in inventories for configuration
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | 2 | Evaluate the impact to downstream processes (internal and external) for voluntary reorganization processing changes
1 | Identify announcement systems used for ex-date notifications |  |  | 3 | Determine responsibility for voluntary reorganization process changes (proprietary vs. external vendor and service bureau)
2 | Determine impact to ex-date notifications and announcement systems for T+1 settlement |  |  | 4 | Coordinate voluntary reorganization processing changes with internal and external stakeholders
3 | Coordinate ex-date notification and announcement system changes with internal and external stakeholders |  |  | 5 | Develop test plans for voluntary reorganization processing applications and voluntary reorganization event processing
4 | Develop ex-date notification and announcement system test plans |  |  | 6 | Schedule and execute changes related to voluntary reorganization processing
5 | Schedule and execute announcement system changes
6 | Communicate changes to ex-date notifications and announcement system changes to external organizations |  |  | 4.3.2.C. Activities to Update Internal Processing Systems that Consume Cover/Protect Dates
|  |  |  | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
4.3.1.C. Activities to Modify Internal Processing Systems that Calculate Ex-Dates |  |  |  | 1 | Ensure that systems and reference data related to cover/protect date calculations are included in inventories for configuration
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | 2 | Evaluate the impact on downstream processes (internal and external) for system and process changes related to cover/protect date calculations
1 | Ensure that systems and reference data related to ex-date calculations are included in inventories for configuration |  |  | 3 | Determine responsibility for cover/protect date calculation changes (proprietary vs. external vendor and service bureau)
2 | Evaluate the impact on downstream processes (internal and external) for system and ex-date |  |  | 4 | Coordinate changes with internal and external stakeholders
3 | Determine responsibility for ex-date calculation changes (proprietary vs. external vendor and service bureau) |  |  | 5 | Develop internally calculated cover/protect date test plan
4 | Coordinate changes with internal and external stakeholders |  |  | 6 | Schedule and execute changes related to internal cover/protect date calculations
5 | Develop internally calculated ex-date test plans (consider how to make changes on T+1 migration date while continuing T+2 settlement operations)
6 | Schedule and execute changes related to internal ex-date calculations |  |  | 4.3.2.D. Activities to Adjust Stock Record Platforms as Necessary
|  |  |  | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
4.3.1.D. Activities to Adjust Due Bill Processing |  |  |  | 1 | Ensure that systems and reference data related to stock record platforms are included in inventories for configuration
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | 2 | Evaluate the impact on downstream processes (internal and external) for system and process changes related to modification of stock record platforms
1 | Ensure that systems and reference data related to due bill processing are included in inventories for configuration |  |  | 3 | Determine responsibility for stock record changes (proprietary vs. external vendor and service bureau)
2 | Determine changes required for due bill processing |  |  | 4 | Coordinate stock record changes with internal and external stakeholders
3 | Coordinate due bill processing changes with internal and external stakeholders |  |  | 5 | Develop internally calculated stock record test plan
4 | Develop test plan for due bill processing |  |  | 6 | Schedule and execute changes related to modification of stock record platforms
5 | Schedule and implement due bill processing changes
4.3.1.E. Activities to Modify Interim Accounting Processes
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
1 | Ensure that systems and reference data related to interim accounting are included in inventories for configuration
2 | Evaluate the impact on downstream processes (internal and external) for interim accounting process changes
3 | Determine responsibility for interim accounting process changes (proprietary vs. external vendor and service bureau)
4 | Coordinate interim accounting process changes with internal and external stakeholders
5 | Develop interim accounting testing plans
6 | Schedule and execute changes related to interim accounting

## Documentation
Update External Client-Facing Documentation |  |  |  | Internal Documentation |  |  |  | Customer and Staff Education
5.3.1.A. Activities to Update External Client-Facing Documentation |  |  |  | 5.3.2.A. Activities to Update External Client-Facing Documentation |  |  |  | 5.3.3.A. Activities to Educate Customers and Staff on T+1 Settlement
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
1 | Inventory external client-facing documentation that references T+2 settlement, including electronic documents and website information |  |  | 1 | Identify and inventory sources for operating procedures and control documentation |  |  | 1 | Identify customers and staff who require education related to T+1 implementation
2 | Inventory static data resources used for auto-populating documentation that references T+2 settlement |  |  | 2 | Determine operating procedures and control documentation that references T+2 settlement |  |  | 2 | Determine if education materials need to be updated or if new education materials need to be created.
3 | Determine which identified documents need to be updated |  |  | 3 | Assess changes required to operating procedures and control documentation |  |  | 3 | Assess changes to staff training materials
4 | Create master list of required documentation changes |  |  | 4 | Coordinate changes with internal and external stakeholders |  |  | 4 | Assess changes to customer educational materials
5 | Coordinate documentation changes with internal and external stakeholders |  |  | 5 | Schedule and execute required changes to identified operating procedures and control documentation |  |  | 5 | Develop a training plan to ensure staff are adequately trained prior to T+1 conversion
6 | Schedule and execute identified changes to documentation |  |  | 6 | Document and track changes to documentation to ensure completeness |  |  | 6 | Develop a communications plan to address customer needs
7 | Cross-reference updates with master list of required documentation changes to ensure accuracy and completeness | [6 empty] | 7 | Create or update materials for staff and customer education
[8 empty] | 8 | Train staff for T+1 implementation
5.3.1.B. Activities to Update External Service Agreement Documentation | [7 empty] | 9 | Distribute T+1 settlement education material to customers
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
1 | Inventory vendor and service bureau documentation that references a two-day settlement period, including agreements, service descriptions, product guides, and fee schedules
2 | Update external vendor and service bureau documentation for a one-day settlement
3 | Review, approve, re-negotiate, and re- authorize changes to documentation as necessary
4 | Test the execution of updated documentation in the delivery and pricing of services
5.3.1.C. Activities to Determine Impact of E-Delivery for Client Groups
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
1 | Inventory vendor and service bureau documentation that is required to be delivered to clients, including agreements, service descriptions, product guides, and fee schedules
2 | Determine e-delivery procedures and documentation that references T+1 settlement
3 | Assess changes required to e-delivery procedures and documentation
4 | Coordinate changes with internal and external stakeholders
5 | Coordinate changes with client groups
6 | Schedule and execute required changes to identified e-delivery procedures and documentation
7 | Test the execution of updated e-delivery for client groups

## Securities Lending
Securities Lending Processes and Procedures |  |  |  | Stock Loan Recall |  |  |  | Margin Calculations Processes |  |  |  | Margin Calculations Processes |  |  |  | Regulatory Considerations
6.3.1.A. Activities for Determining Impact on Securities Lending Processes and Procedures |  |  |  | 6.3.2.A. Activities to Align to Updated Stock Loan Recall Timing Changes |  |  |  | 6.3.3.A. Activities to Update Margin Calculation Processes |  |  |  | 6.3.4.A. Activities to Update Master Securities Loan Agreement |  |  |  | 6.3.5.A. Activities for Assessing Regulatory Considerations related to Securities Lending
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
1 | Inventory securities lending processes and procedures documentation (completeness check) |  |  | 1 | Determine required changes to stock loan recall processes for migration to T+1 settlement |  |  | 1 | Ensure that systems and reference data related to margin calculations are included in inventories for configuration |  |  | 1 | Inventory Master Securities Loan Agreements that reference T+2 settlement |  |  | 1 | Assess rule changes for securities lending
2 | Ensure that systems and reference data related to securities lending are included in inventories for configuration |  |  | 2 | Determine responsibility for stock loan recall timing changes |  |  | 2 | Evaluate the impact on downstream processes (internal and external) for system and process changes related to margin calculations |  |  | 2 | Assess changes required to MSLAs |  |  | 2 | Ensure that systems and reference data impacted by rule changes are included in inventories for configuration
3 | Assess the impact of required changes to upstream and downstream systems |  |  | 3 | Coordinate changes with internal and external stakeholders |  |  | 3 | Determine responsibility for margin calculation changes |  |  | 3 | Coordinate changes to MSLAs with internal and external stakeholders |  |  | 3 | Determine process changes required to maintain compliant with rule changes
4 | Determine responsibility for securities lending changes (proprietary vs. external vendor and service bureau) |  |  | 4 | Develop stock loan recall timing changes test plan |  |  | 4 | Coordinate changes with internal and external stakeholders |  |  | 4 | Schedule and execute identified changes to MSLAs |  |  | 4 | Coordinate changes with both internal and external parties
5 | Coordinate changes with internal and external stakeholders |  |  | 5 | Schedule and execute changes prior to migration to T+1 settlement |  |  | 5 | Develop margin calculation test plan |  |  | 5 | Document and track changes to MSLAs to ensure completeness |  |  | 5 | Develop rule change test plans
6 | Develop exercise and assignment test plans | [6 empty] | 6 | Schedule and execute changes related to margin calculations | [6 empty] | 6 | Schedule and execute changes for system changes
7 | Schedule and execute system, process, and documentation changes | [14 empty] | 7 | Update operational policies and procedures as applicable for each rule change
8 | Review effective controls to prevent issues (e.g., inadvertent data disclosure, client confidential breach) | [14 empty] | 8 | Update compliance policies and procedures as applicable for each rule change
[16 empty] | 9 | Update regulatory policies and procedures as applicable for each rule change

## Prime Brokerage
Review Client Onboarding Documentation and Processing Dependencies
7.3.1.A. Activities to Review Prime Broker Disaffirmation Timelines
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
1 | Ensure that systems and reference data related to prime broker disaffirmation are included in inventories for configuration
2 | Examine upstream system, data, and process changes to ensure that they do not interfere with the process for prime broker disaffirmation
3 | Determine changes required to processes related to prime broker disaffirmation
4 | Coordinate changes to processes related to prime broker disaffirmation with internal and external stakeholders
5 | Schedule and execute process changes for prime broker disaffirmation
7.3.1.B. Activities to Review Prime Broker Affirmation Timelines
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
1 | Ensure that systems and reference data related to prime broker affirmation are included in inventories for configuration
2 | Examine upstream system, data, and process changes to ensure that they do not interfere with the process for prime broker affirmation
3 | Determine changes required to processes related to prime broker affirmation
4 | Coordinate changes to processes related to prime broker affirmation with internal and external stakeholders
5 | Schedule and execute process changes for prime broker affirmation

## Funding and Liquidity
Liquidity and Collateral Management |  |  |  | Forex Considerations and Funding |  |  |  | Intraday & End of Day DTCC Settlement Processing
8.3.1.A. Activities to Assess Liquidity and Collateral Management |  |  |  | 8.3.2.A. Activities to Assess Forex Considerations and Funding |  |  |  | 8.3.3.A. Activities to Assess Intraday & End of Day DTCC Settlement Processing
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
1 | Determine if strategies, policies, or practices to manage liquidity risk need to change based on the shortened settlement cycle |  |  | 1 | Identify changes to market synchronization for T+1 settlement cycle |  |  | 1 | Ensure that systems and reference data related to intraday & end of day DTCC settlement processing are included in inventories for configuration
2 | Determine impacts to projection of cash flows |  |  | 2 | Assess impact of market synchronization changes to foreign exchange and funding |  |  | 2 | Examine upstream system, data, and process changes to ensure that they do not interfere with intraday & end of day DTCC settlement processing
3 | Determine if T+1 settlement will impact the collateral management process |  |  | 3 | Determine changes required due to T+1 implementation |  |  | 3 | Determine process changes required for intraday & end of day DTCC settlement
4 | Determine if changes to collateral management systems are required due to shortened settlement cycle |  |  | 4 | Coordinate identified changes with internal and external stakeholders |  |  | 4 | Coordinate changes to processes related to intraday & end of day DTCC settlement with internal and external stakeholders
|  |  |  | 5 | Schedule and execute identified changes |  |  | 5 | Develop test plans for intraday & end of day DTCC settlement processing
[8 empty] | 6 | Schedule and execute process changes for intraday & end of day DTCC settlement

## Additional Considerations
Global Consideration |  |  |  | Options Exercise and Assignment |  |  |  | Primary Offerings |  |  |  | Reconciliations for Errors / Fails |  |  |  | Buy-Side Considerations
9.3.1.A. Activities to Review Processes for Global Considerations |  |  |  | 9.3.2.A. Activities to Assess Options Exercise and Assignment Processes |  |  |  | 9.3.3.A. Activities to Assess Primary Offerings |  |  |  | 9.3.4.A. Activities to Assess Reconciliation Processes for Errors / Fails |  |  |  | 9.3.5.A. Activities to Assess Buy-Side Considerations
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems | # | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
1 | Identify changes to market synchronization for T+1 settlement cycle |  |  | 1 | Inventory exercise and assignment processes and documentation (completeness check) |  |  | 1 | Determine required changes for primary offerings required for migration to T+1 |  |  | 1 | Determine the redundant manual touchpoints and illiquid securities in the current system |  |  | 1 | Revisit the internal processes, begin impact analysis, and look for investment opportunities that can accelerate change
2 | Assess impact of market synchronization changes to foreign exchange, foreign investment, and cross-border transaction processing, procedures, and policy documentation |  |  | 2 | Ensure that systems and reference data related to options exercise and assignment are included in inventories for configuration |  |  | 2 | Accelerate documentation procedures required to close primary offerings |  |  | 2 | Automate the processes and streamline communication channels |  |  | 2 | Identify processes that can be automated and controls that need to be updated
3 | Review issuance and cancellation procedures around ADR processing |  |  | 3 | Assess the impact of required changes to upstream and downstream systems |  |  | 3 | Coordinate changes with internal and external stakeholders |  |  | 3 | Ensure seamless flow of trade instruction from one counterparty to another |  |  | 3 | Update systems to incorporate new recordkeeping changes related to trade allocation, affirmation, and confirmation
4 | Determine changes required due to T+1 implementation |  |  | 4 | Determine responsibility for exercise and assignment changes (proprietary vs. external vendor and service bureau) |  |  | 4 | Develop test plans to check the robustness of the system in handling operational issues |  |  | 4 | Coordinate changes amongst all stakeholders |  |  | 4 | Schedule and execute system, process, and documentation changes
5 | Coordinate identified changes with internal and external stakeholders |  |  | 5 | Coordinate changes with internal and external stakeholders |  |  | 5 | Schedule and execute new systems for primary offerings to cater to the new compressed timeframe of T+1 |  |  | 5 | Test the new systems in place |  |  | 5 | Test the processes and assess to solve outstanding issues
6 | Schedule and execute identified changes |  |  | 6 | Develop exercise and assignment test plans | [6 empty] | 6 | Schedule and execute system changes
|  |  |  | 7 | Schedule and execute system, process, and documentation changes

## Testing and Migration
Develop Internal and Industry Test Plan
11.3.1.B. Activities to Develop Test Plans
# | Implementation Steps | Organization Participants (Front, Middle, Back, IT, Vendor) | Supporting Systems
1 | Draft test plan
2 | Confirm readiness with vendors and service bureaus to determine static data and software field updates for internal systems
3 | Develop internal testing scenarios and data
4 | Conduct internal testing and evaluate results
5 | Coordinate external testing with internal and external stakeholders
6 | Conduct external testing and evaluate results
7 | Develop the organization’s plan to participate in industry testing
8 | Participate (if applicable) in DTCC testing prior to industry test
9 | Conduct post-migration testing activities

## Revision History
Version | Publish Date | Description
1 | 2022-07-28 | Initial publication